## Sheet1
Tasklist |  |  |  | Key
TODO | DOING | DONE | Cancelled | Easy to do (0-1 day)
Create first level design | Write Daily Dairy | Create Scrum Spreadsheet | Create "game idea 1" - Dodgeball | Somewhat challenging (1-3 days)
Model first level design in Unity | Create Ball Throwing Momentum game | Create Github Repo |  | Difficult (3+ days)
Create custom assets if needed | Creating tasklist | Identify outline for game
Build to executable outside of Unity editor | Model Throwing Physics in Unity | Write Outline Spec
Create Menu for game | Model Collision recognition in Unity | Added VRTK + Steam VR to Unity Project
Find/Record audio elements